## Gantt Chart
NutriFit GANTT CHART
Project Title |  | Software Project Proposal
Project Manager |  | Max / Manahil
Course Name |  | CM2020 Agile Software Projects
Tutor Group Number |  | Team 20 ( Group 6)
Number of Team Members |  | 5
Task Number | Task Title | Task Owner | Start Date | Due Date | Duration (Days) | Dependency |  | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22
Status
1 | Project Conception and Initiation | [6 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1.1 | Channel Creation ( Slack) | Manahil | 2024-11-10 | 2024-11-10 | 0 | - | Completed | bar: S
1.1.1 | Version Control Setup (GitHub) | Manahil | 2024-11-11 | 2024-11-11 | 0 | - | Completed | bar: M
2 | Project Definition and Planning
2.1 | Aims/Objectives | All | 2024-11-24 | 2024-11-25 | 1 | - | Not started
2.2 | Task Allocation | Bright | 2024-11-19 | 2024-11-23 | 3 | Aims/Obj | In Progress
2.3 | Project Board (GitHub) | Max | 2024-11-20 | 2024-11-24 | 4 | GitHub | Not started
2.4 | Project Specification | Rasha | 2024-11-20 | 2024-11-24 | 4 | Aims/Obj | In Progress
2.5 | Project Scope | Lukemaan | 2024-11-20 | 2024-11-24 | 4 | Aims/Obj | Not started
2.6 | Project Requirements | Manahil | 2024-11-20 | 2024-11-24 | 4 | Aims/Obj | Not started
3 | Project Market Research
3.1 | Literature | Manahil | 2024-11-20 | 2024-12-01 | 11 | - | In Progress
3.2 | Conduct User Interviews | All | 2024-11-20 | 2024-12-01 | 11 | - | Not started
3.2.1 | Analyze Competitor Apps | Bright | 2024-11-20 | 2024-12-01 | 11 | - | In Progress
3.2.2 | Create User Personas | Max | 2024-11-20 | 2024-12-01 | 11 | Interviews | Not started
3.3 | Write User Stories | All | 2024-11-20 | 2024-12-01 | 11 | Personas | Not started
4 | Project Design
4.1 | Create Wireframes | Lukemaan | 2024-11-20 | 2024-11-24 | 4 | User Stories | Not started
4.2 | Design Low-Fidelity Prototypes | Max | 2024-11-20 | 2024-11-24 | 4 | User Stories | Not started
5 | Project Assumption Testing
5.1 | User Motivation | All | 2024-12-05 | 2024-12-08 | 3 | Interviews | Not started
5.2 | User Feedback | All | 2024-12-05 | 2024-12-08 | 6 | Prototypes | Not started
5,2.1 | User Preferences | All | 2024-12-05 | 2024-12-08 | 6 | User Feedback | Not started
5,2.2 | User Acceptance | All | 2024-12-05 | 2024-12-08 | 6 | User Preferences | Not started
6 | Project Analysis/Evaluation
6.1 | Project Data Collection | All | 2024-12-09 | 2024-12-15 | 6 | - | Not started
6.2 | Project Feedback | All | 2024-12-09 | 2024-12-15 | 6 | User Acceptance | Not started
6.3 | Project Adjustments | All | 2024-12-09 | 2024-12-15 | 6 | Feedback | Not started
6.4 | Project Success | All | 2024-12-09 | 2024-12-15 | 6 | User Acceptance | Not started
6.4 | Project Limitations | All | 2024-12-09 | 2024-12-15 | 6 | User Feedback | Not started
6.4 | Project Report | Manahil/Max | 2024-12-16 | 2024-12-22 | 6 | All | Not started
Project Devlopment Concept
6,4.2 | Frontend Angular/ UI Design and Implementation | Manahil | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.3 | Frontend Angular /Authentication Pages | Rasha | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.4 | Frontend Angular / Fitness Tracking Dashboard | Bright | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.5 | Frontend Angular / Recipe Recommendation Page | Lukemaan | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.6 | Frontend Angular/ API Integration and State Management | Max | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.7 | Backend PEAN / User Authentication | Rasha | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.8 | Backend PEAN / Fitness Tracking API | Bright | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.9 | Backend PEAN / Recipe Recommendation API | Lukemaan | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.10 | Backend PEAN / Database Schema Design and management | Manahil | 2024-11-25 | 2024-12-08 | 13 | Wireframes | Not started
6,4.11 | Backend PEAN / API Testing and Integration | Max | 2024-12-25 | 2024-12-08 | 13 | Wireframes | Not started